## Copy of Sheet1
Task | Comments | UI tasks | Estimate | Dev tasks | Estimate | Priority | Comment from Oksana
Home page |  | done |  | done
Solutions | mostly done
What is iCure |  | done |  | done
For Primary care EHR (inner page) |  | no content |  |  |  |  | remove the More button, we will add this content later
for Patient Medical Records (inner page) |  | no content |  |  |  |  | remove the More button, we will add this content later
for Medical Devices (inner page) |  | no content |  |  |  |  | remove the More button, we will add this content later
for Healthcare apps (inner page) |  | no content |  |  |  |  | remove the More button, we will add this content later
for Public Health (inner page) |  | no content |  |  |  |  | remove the More button, we will add this content later
Pricing |  | done |  | done
Case studies |  | no content |  |  |  | 1 | make it greyed out in the menu
Training and Deployment |  | no content |  |  |  |  | make it greyed out in the menu
Technology | mostly done
Trust and Privacy Protection |  | done |  | done
Data Model and Interoperability |  | done |  | done
Synchronization |  | done |  | done
Data Sharing |  | done |  | done
FHIR Data Model |  | done |  | done
Hybrid Cloud Support |  | done |  | done
iCure Modules (scheme) |  | done |  | done
FHIR Data Model (inner page) |  | no content |  |  |  |  | we will link to the technical documentation page, please add the generic link http://icure.dev to each of them (we will make the change after we come correctily all the domains). Git book w
FPatient Summary File (SumEHR, others) |  | no content |  |  |  |  | we will link to the technical documentation page, please add the generic link http://icure.dev to each of them (we will make the change after we come correctily all the domains). Git book w
Secure Mailing System (inner page) |  | no content |  |  |  |  | we will link to the technical documentation page, please add the generic link http://icure.dev to each of them (we will make the change after we come correctily all the domains). Git book w
Invoicing Engine (inner page) |  | no content |  |  |  |  | we will link to the technical documentation page, please add the generic link http://icure.dev to each of them (we will make the change after we come correctily all the domains). Git book w
eConsent (inner page) |  | no content |  |  |  |  | we will link to the technical documentation page, please add the generic link http://icure.dev to each of them (we will make the change after we come correctily all the domains). Git book w
ePrescription (inner page) |  | no content |  |  |  |  | we will link to the technical documentation page, please add the generic link http://icure.dev to each of them (we will make the change after we come correctily all the domains). Git book w
Medication (inner page) |  | no content |  |  |  |  | we will link to the technical documentation page, please add the generic link http://icure.dev to each of them (we will make the change after we come correctily all the domains). Git book w
Data Hosting (inner page) |  | no content |  |  |  |  | we will link to the technical documentation page, please add the generic link http://icure.dev to each of them (we will make the change after we come correctily all the domains). Git book w
Forms (inner page) |  | no content |  |  |  |  | we will link to the technical documentation page, please add the generic link http://icure.dev to each of them (we will make the change after we come correctily all the domains). Git book w
Medication (inner page) |  | no content |  |  |  |  | we will link to the technical documentation page, please add the generic link http://icure.dev to each of them (we will make the change after we come correctily all the domains). Git book w
iCureAcess app (inner page) |  | no content |  |  |  |  | we will link to the technical documentation page, please add the generic link http://icure.dev to each of them (we will make the change after we come correctily all the domains). Git book w
Graphical Interface (inner page) |  | no content |  |  |  |  | we will link to the technical documentation page, please add the generic link http://icure.dev to each of them (we will make the change after we come correctily all the domains). Git book w
Technical Documentation (based on gitbook)
Technology | mostly done
Blog |  | done |  | done |  | high | I will provide you the text of the press release, will need your help to make the post from it please use another news from last year to publish there as well: https://icure.io/euvsvirus_pressrelease/ - reuse the text and graphic, change the style
Technical documentation
Whitepapers |  | no content
Reports |  | no content
About us
Team | only UI | done |  | till 24/03 | 2h
Our values | only UI | done |  | till 24/03 | 2h
Supporters | only UI | done |  | till 24/03 | 2h
[6 empty] | high | please add the page into menu as discussed at the previous call, I will provide the content for it
Schedule a demo |  | done
Other tasks
pptx elements for presentations |  | done
Linked in cover (adobe XD) |  | in process |  |  |  | high | i need the cover urgently please, I was giving the comments already
Figma elements UI Kit | [5 empty] | low
Post template (adobe XD) |  | in process |  |  |  | high
Stories template (adobe XD) |  | in process |  |  |  | high
Add images (shphere and honeycomb) as PNG |  |  |  | 22/03 | 1h | high
Sphere block |  |  |  | till 24/03 | 2h
Honeycomb block |  |  |  | till 24/03 | 20h
email template | [5 empty] | high | NEW - can you please create an email template that i could use for the mailing campaings (something simple and working well for the email sytems ) I will use it to send the monthy news etc